## Sheet1
Risk ID | Category | Risk Description | Likelihood | Impact | Risk Score=D2*E2 | Risk Level | Risk Owner | Treatment | Mitigation Action | Status | Review Date
RK-001 | Cybersecurity | Phishing attack compromises employee credentials giving unauthorized access to payment systems | 4 | 5 | 20 | Critical | IT Security Manager | Mitigate | Deploy MFA on all systems; run quarterly phishing simulations | In Progress | 2026-09-30
RK-002 | Compliance | Failure to comply with RBI data localization requirements resulting in regulatory fines | 3 | 4 | 12 | High | Compliance Officer | Mitigate | Engage RBI compliance consultant; implement data localization controls | Open | 2026-08-31
RK-003 | Third-party | Payment gateway vendor suffers outage causing transaction processing failure for all merchants | 3 | 5 | 15 | Critical | Operations Manager | Transfer | Establish SLA with backup payment gateway vendor; buy cyber insurance | In Progress | 2026-09-30
RK-004 | Cybersecurity | Unpatched vulnerabilities in web application allow SQL injection attack on customer database | 3 | 5 | 15 | Critical | IT Security Manager | Mitigate | Conduct quarterly VAPT; implement WAF on web application | Open | 2026-07-31
RK-005 | Operational | Key developer resigns with no knowledge transfer causing critical system failure | 2 | 4 | 8 | Medium | HR Manager | Mitigate | Enforce knowledge transfer policy; cross-train two backup engineers | Open | 2026-10-31
RK-006 | Physical | Unauthorized physical access to server room results in hardware theft or tampering | 2 | 3 | 6 | Medium | Facilities Manager | Mitigate | Install biometric access control; add CCTV in server room | In Progress | 2026-12-31
RK-007 | Compliance | DPDP Act non-compliance due to missing data privacy consent mechanisms | 4 | 4 | 16 | Critical | Legal & Compliance Head | Mitigate | Implement consent management system; conduct DPDP gap assessment | Open | 2026-07-31
RK-008 | Cybersecurity | Insider threat from privileged admin misusing access to steal customer payment data | 2 | 5 | 10 | High | CISO | Mitigate | Enforce least privilege access; deploy PAM tool; audit admin logs monthly | Open | 2026-09-30
RK-009 | Third-party | Cloud provider (AWS) regional outage causes complete platform downtime | 2 | 5 | 10 | High | Cloud Infrastructure Lead | Mitigate | Enable multi-region AWS failover; review and update DR plan | In Progress | 2026-09-30
RK-010 | Operational | DDoS attack overwhelms payment API causing merchant transaction failures | 3 | 4 | 12 | High | IT Security Manager | Mitigate | Deploy DDoS protection via AWS Shield; configure rate limiting on API | Open | 2026-08-31

## Risk Heat Map
Shibu Cloud Solutions Pvt Ltd — Risk Heat Map
|  | 1 | 2 | 3 | 4 | 5
| 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 RK-007 | 20 RK-001
Likelihood | 3 | 3 | 6 | 9 | 12 RK-002 RK-010 | 15 RK-003 RK-004
| 2 | 2 | 4 | 6 RK-006 | 8 RK-005 | 10 RK-008 RK-009
| 1 | 1 | 2 | 3 | 4 | 5
|  | Legend |  | Impact →
|  | Low (Score 1–4) | Accept or Monitor annually
|  | Medium (Score 5–9) | Monitor quarterly, assign owner
|  | High (Score 10–14) | Immediate mitigation plan required
|  | Critical (Score 15–25) | Escalate to leadership immediately